## Team
Sl No | Library Name | Link | Type of Library | Language | Developer | Co-Developer | Mentor | Status | Team | Remarks | Open Source Date
1 | UnifiedContactPicker | https://github.com/quiin/UnifiedContactPicker | Layout | Java | Rejeesh/Niveda | B Manjunatha | Venkata Sreeni | Release to Maven | I&M Team
2 | FlexibleCalendar | https://github.com/p-v/FlexibleCalendar | UI | Java | Indrajit | Niveditha | Venkata Sreeni | Release to Maven | I&M Team
3 | SpannableTextView | https://github.com/milaptank/SpannableTextView | Functional | Java | Sujith | B Manjunatha | Venkata Sreeni | Release to Maven | I&M Team
4 | Springy_Facebook_Rebound | https://github.com/SalmanZach/Springy_Facebook_Rebound | Animation | Java |  |  | Kanak Sony | Stopped | NA | Already ported
5 | SlidingIntroScreen | https://github.com/MatthewDavidBradshaw/SlidingIntroScreen | Animation | Java |  |  | Sharath K S | Analysis | TBD
6 | InfiniteScroll | https://github.com/pwittchen/InfiniteScroll | Functional | Java | Praveen | Subba Reddy | Subba Reddy | Testing in-progress | I&M Team
7 | FlexibleSearchBar | https://github.com/yuqirong/FlexibleSearchBar | Layout | Java | Vijay Kumar | Sreeni/Indra | Venkata Sreeni | Release to Maven | I&M Team
8 | multiple-media-picker | https://github.com/erikagtierrez/multiple-media-picker | Functional | Java | Jaya Shankar | B Manjunatha | Venkata Sreeni | Release to Maven | I&M Team
9 | DropIndicator | https://github.com/Ulez/DropIndicator | Animation | Java | Zunaid | Subba Reddy | Subba Reddy | Testing in-progress | I&M Team
10 | ZGallery | https://github.com/mzelzoghbi/Zgallery | Layout | Java | Sahana |  | Gowtham G S | Testing in-progress | Partners | Testing phase
11 | Android-SocialButtons | https://github.com/championswimmer/Android-SocialButtons | UI | Java | Ashish Prabhakar | Amal Cyriac | Subba Reddy | Development in-progress | I&M Team | Typed array is not implemented fully in HMOS, so we cannot implement same behaviour like android.
12 | TickSeekBar | https://github.com/warkiz/TickSeekBar | Animation | Java | Niveditha | Indrajit | Venkata Sreeni | Release to Maven | I&M Team
13 | Bluetooth-Library | https://github.com/OmarAflak/Bluetooth-Library | Connectivity | Java | Chandrakanth | Subba Reddy | Subba Reddy | Development in-progress | I&M Team | Bluetooth Socket API are in development stage, currently HQ are fixing errors and as per the current info they will share the latest api’s by Aug end.
14 | android-swipecards-view | https://github.com/Arjun-sna/android-swipecards-view | Layout | Java | Shubham Karmakar |  | Kanak Sony | Development in-progress | College-Student
15 | amplify | https://github.com/stkent/amplify | Functional | Java | Chirag Bhatt |  | Meghna | Release to Maven | Intern-IIT
16 | Signal strengths | https://github.com/fennifith/SignalStrengths | Connectivity | Java | Mayur | Jawahar | Kathir | Release to Maven | I&M Team
17 | Instalike View | https://github.com/KshitijDroid/InstaLikeView | UI | Java | Samuel Abhishekam M |  | Samuel Abhishekam M | Release to Maven | I&M Team
18 | Android verify | https://github.com/pchmn/AndroidVerify | Form validation | Java | Amit Shekhar |  | Meghna | Release to Maven | Intern-IIT
19 | Circular view pager | https://github.com/sanyuzhang/CircularViewPager | UI | Java | Taha Junaid |  |  | Available for Development | College-Student | Not started. Busy with academic research.
20 | indicator view | https://github.com/KshitijDroid/IndicatorView | UI | Java | Jawahar | Mayur | Kathir | Release to Maven | I&M Team
21 | Richbuttons | https://github.com/ksoichiro/RichButtons | UI | Java |  |  | Sharath K S | Available for Development | TBD
22 | FastScroll-RecyclerView | https://github.com/jaredrummler/FastScroll-RecyclerView | UI | Java | Jatin |  | Kamal Shree | Development Completed | Intern-IIT | Development completed and code submitted to github. https://github.com/jjatinggoyal/assessment. Testing is pending. Some other person need to do Testing.
23 | CircularDialogs | https://github.com/HassanUsman/CircularDialogs | UI | Java | Soham |  | Kanak Sony | Release to Maven | Intern-IIT
24 | StripedProcessButton | https://github.com/nikartm/StripedProcessButton | UI | Java | Alpesh kaushal |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
25 | SmartyToast | https://github.com/amanjeetsingh150/SmartyToast | Animation | Java | Sravani/Zunaid | Subba reddy | Subba reddy | Code submission to github | I&M Team
26 | Custom-Calendar-View | https://github.com/npanigrahy/Custom-Calendar-View | UI | Java | Chokkaku Chakradhar |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
27 | HorizontalPicker | https://github.com/jhonnyx2012/HorizontalPicker | Layout | Java |  |  | Sharath K S | Available for Development | TBD
28 | MaterialCalendar | https://github.com/jMavarez/MaterialCalendar | UI | Java | Mamilla Sai Yashwanth |  | Sharath K S | Release to Maven | Intern-IIT
29 | MayI-Java | https://github.com/ThanosFisherman/MayI-Java | Functional | Java | YashRaj Gupta |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
30 | croperino | https://github.com/mike14u/croperino | Functional | Java |  |  | Sharath K S | Available for Development | TBD | Camera access is not there in emulator
31 | view-effects | https://github.com/mirrajabi/view-effects | UI | Java | Nivasa Manduva/Vinay | Subba Reddy | Subba reddy | Code submission to github | I&M Team
32 | Blurry | https://github.com/wasabeef/Blurry | Functional | Java | Vinayak | Subba reddy | Subba reddy | Stopped | I&M Team | These framework api’s are not integrated and also stopped in android.
33 | MaterialIcon | https://github.com/IvBaranov/MaterialLetterIcon | UI | Java | Shrey shrivastava |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
34 | expandable-recycler-view | https://github.com/thoughtbot/expandable-recycler-view | UI | Java | Anshul Goel |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
35 | PhotoView | https://github.com/Baseflow/PhotoView | Functional | Java |  |  | Sharath K S | Stopped | NA | Similar lib is getting ported
36 | android-lite-go | https://github.com/litesuits/android-lite-go | Functional | Java | Mahesh | Harit Jaiswal | Meghna | Release to Maven | Intern-IIT
37 | HDImageView | https://github.com/EvilBT/HDImageView | UI | Java | Shivam Jamaiwar |  | Kanak Sony | Development in-progress | Partners | Yet to start ttesting. Having laptop issue. Code submitted to github: https://github.com/applibgroup/Pan_and_Zoom
38 | PinchToZoom | https://github.com/martinwithaar/PinchToZoom | Functional | Java | Dakarapu Bharath | Mamilla Sai Yashwanth | Sharath K S | Release to Maven | Intern-IIT
39 | AnchorSheetBehavior | https://github.com/skimarxall/AnchorSheetBehavior | Layout | Java | Yogesh |  | Kanak Sony | Release to Maven | Intern-IIT
40 | XRadarView | https://github.com/hust201010701/XRadarView | UI | Java | Shivam Jamaiwar |  | Kanak Sony | Release to Maven | Partners
41 | WheelPicker | https://github.com/open-android/WheelPicker | UI | Java | Jaswanth |  | Kanak Sony | Release to Maven | Intern-IIT
42 | ImageZoom | https://github.com/okaybroda/ImageZoom | Functional | Java | Komal Narayan |  | Kanak Sony | Release to Maven | Intern-IIT
43 | RxTuples | https://github.com/pakoito/RxTuples | Functional | Java | Harit Jaiswal |  | Meghna | Released to HPM | Intern-IIT
44 | Pretty-Painter | https://github.com/devolonter/Pretty-Painter | Tool | Java |  |  | Sharath K S | Available for Development | TBD
45 | Diffre | https://github.com/rakshakhegde/Diffre | UI | Java | Mahesh |  | Meghna | Release to Maven | Intern-IIT
46 | MaterialFancyButtons | https://github.com/joielechong/MaterialFancyButtons | UI | Java | Mahesh | Harit Jaiswal | Meghna | Release to Maven | Intern-IIT
47 | RoundedImageView | https://github.com/vinc3m1/RoundedImageView | Functional | Java |  |  | Sharath K S | Stopped | NA | Already ported
48 | TAndroidLame | https://github.com/naman14/TAndroidLame | Tool | Java |  |  | Sharath K S | Analysis | TBD | Take opinion from MultiMedia team
49 | vlc-android | https://github.com/mstorsjo/vlc-android | Tool | Java |  |  | Sharath K S | Analysis | TBD | Complex library, take opinion from MultiMedia team
50 | PullSeparateListView | https://github.com/chiemy/PullSeparateListView | Layout | Java |  |  | Sharath K S | Stopped | NA
51 | ScrollerCalendar | https://github.com/guanchao/ScrollerCalendar | UI | Java |  |  | Sharath K S | Stopped | NA
52 | Meshenger | https://github.com/dakhnod/Meshenger | Tool | Java |  |  | Sharath K S | Analysis | TBD | Distrubuted messenger functionality to be checked
53 | iQuePhoto | https://github.com/iQueSoft/iQuePhoto | Tool | Java |  |  | Sharath K S | Analysis | TBD | Photo Editor adding text and image/icon. Rotate
54 | Navigation & Drawer Layout | Self developed modules |  | Java |  |  | Sharath K S | Analysis | TBD
55 | HomeScreen | Self developed modules |  | Java |  |  | Sharath K S | Analysis | TBD
56 | Facebooklike Listview | Self developed modules |  | Java |  |  | Sharath K S | Analysis | TBD
57 | SlideShow Layout | Self developed modules |  | Java |  |  | Sharath K S | Analysis | TBD
58 | EmojiConverter | https://github.com/AnkitKiet/EmojiConverter | Functional | Java | Muhammed Fazil K |  | Samuel Abhishekam M | Release to Maven | College-Student | Working on library
59 | Wiggle | https://github.com/kubode/Wiggle | Functional | Java |  |  | Sharath K S | Stopped | NA | Very Small Lib with not useful Business usecase
60 | FeatureAdapter | https://github.com/groupon/FeatureAdapter | Functional | Java |  |  | Sharath K S | Stopped | NA
61 | AndroidUtilities | https://github.com/mattbradshaw001/AndroidUtilities | Tool | Java |  |  | Sharath K S | Analysis | TBD | Less Usage of lib and Effort is more
62 | convalida | https://github.com/wellingtoncosta/convalida | UI | Java |  |  | Sharath K S | Available for Development | TBD | DataBinding functionality is not working Need to check how to implement withtout Databinding
63 | Android-DraggableGridViewPager | https://github.com/zzhouj/Android-DraggableGridViewPager | Layout | Java |  |  | Sharath K S | Analysis | TBD | We have analyzed this before that few API's are not available Need to analyze how we can do this in Harmony using platform API's
64 | Qiantao94 | https://github.com/qiantao94/RxBle | Functional | Java |  |  | Kanak Sony | Stopped | NA | Only API's are there it can be implemented Normally
65 | android-audio-sensei | https://github.com/rygelouv/android-audio-sensei | Functional | Java |  |  | Samuel Abhishekam M | Stopped | NA | Main functionality is not working with Android code
66 | valifi | https://github.com/mlykotom/valifi | Form validation | Java | Amit Shekhar |  | Meghna | Release to Maven | Intern-IIT
67 | Card-viewFix | https://github.com/bigmanLau/CardviewFix | Layout | Java | Prateek Aher |  | Gowtham G S | Development in-progress | External | Started with library, but busy with work.
68 | Realm-java | https://github.com/realm/realm-java | Database | Java | Ashish Kumar |  | Gowtham G S | Development in-progress | External | Working with library
69 | RxDownload | https://github.com/ssseasonnn/RxDownload | Tool | Java | Devang Vijay |  | Gowtham G S | Development in-progress | External | Not Started, busy with placement drive.
70 | slidetoact | https://github.com/cortinico/slidetoact | UI | Kotlin | Shivam Jamaiwar |  | Kanak Sony | Code submission to github | Partners | Working on library
71 | SuperSLiM | https://github.com/TonicArtos/SuperSLiM | UI | Kotlin | Balaaji Muthukumar |  | Gowtham G S | Development in-progress | External | Working on Kotlin library, He will ask if he will face issues. Have been told to work on Contest Library.
72 | flexadapter | https://github.com/ajalt/flexadapter | Layout | Kotlin |  |  | Sharath K S | Available for Development | TBD | Kotlin Library
73 | PickPhotoSample | https://github.com/werbhelius/PickPhotoSample | Functional | Kotlin |  |  | Sharath K S | Available for Development | TBD | Kotlin Library
74 | HorizontalWheelView | https://github.com/shchurov/HorizontalWheelView | UI | Java | Sambhav Kumar Thakur |  | Meghna | Development in-progress | July-Event | Not Interested
75 | erchenger/SizeAdjustingTextView | https://github.com/erchenger/SizeAdjustingTextView | Functional | Java | Sul Tan |  | Sharath K S | Development in-progress | July-Event | No update. Oversea contributor
76 | CircleSeekbar | https://github.com/feeeei/CircleSeekbar | UI | Java | Aravind M |  | Gowtham G S | Development in-progress | July-Event | Not getting enough time to work on Library, but already started working on assigned Library
77 | CalendarDateView | https://github.com/xingxing-yan/CalendarDateView | UI | Java | Karthikeyan K |  | Gowtham G S | Development in-progress | July-Event | Unable to take part in contest because of ongoing placements, but will be able to work on same library after 2 weeks
78 | jackpocket/android_scratchoff | https://github.com/jackpocket/android_scratchoff | UI | Java | Balaaji Muthukumar |  | Gowtham G S | Development in-progress | July-Event | Working on Kotlin library, He will ask if he will face issues. Have been told to work on Contest Library.
79 | lufficc/StateLayout | https://github.com/lufficc/StateLayout | Layout | Java |  |  | Sharath K S | Available for Development | TBD
80 | GuideView | https://github.com/easilycoder/GuideView | UI | Java | Anuj Mathur |  | Gowtham G S | Development in-progress | July-Event | Not getting enough time to work on Library, but already started working on assigned Library
81 | UniversalPickerDialog | https://github.com/stfalcon-studio/UniversalPickerDialog | Layout | Java | Sparsh Singh |  | Gowtham G S | Development in-progress | July-Event | Unable to take part in contest because of work load, but will be working on assigned library
82 | ZzHorizontalProgressBar | https://github.com/zhouzhuo810/ZzHorizontalProgressBar | UI | Java | Thatikonda Yogi Sainadh |  | Gowtham G S | Development in-progress | July-Event | Not Interested
83 | StateManager | https://github.com/alibaba/StateManager | Functional | Java |  |  | Sharath K S | Available for Development | TBD
84 | SharpView | https://github.com/zengzhaoxing/SharpView | UI | Java | Shrey shrivastava |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
85 | ZBanner | https://github.com/likeadog/ZBanner | UI | Java | Akshay Saini |  | Gowtham G S | Development in-progress | July-Event | Working on library
86 | KitKatEmoji | https://github.com/chathudan/KitKatEmoji | Functional | Java |  |  | Sharath K S | Available for Development | TBD
87 | TypefaceHelper | https://github.com/Drivemode/TypefaceHelper | Functional | Java |  |  | Sharath K S | Available for Development | TBD
88 | Forcelayout | https://github.com/kai0masanari/Forcelayout | UI | Java |  |  | Sharath K S | Available for Development | TBD
89 | HeaderView | https://github.com/raphaelbussa/HeaderView | UI | Java | Taha Junaid |  |  | Available for Development | July-Event | Not started with contest library. Busy with academic research.
90 | HijriDatePicker | https://github.com/alhazmy13/HijriDatePicker | Layout | Java |  |  | Sharath K S | Available for Development | TBD
91 | GBSlideBar | https://github.com/edanel/GBSlideBar | Animation | Java | Muhammed Fazil K |  | Samuel Abhishekam M | Development in-progress | July-Event | Working with Emoji Converter
92 | Prefs | https://github.com/GrenderG/Prefs/ | Functional | Java | Nehal Jaisalmeria |  | Gowtham G S | Development in-progress | July-Event | Unable to contribute now because of work load
93 | TextWithImageDrawable | https://github.com/wuseal/TextWithImageDrawable | Layout | Java | Akhil Chandra |  |  | Available for Development | July-Event | Not started
94 | androidmads/SQLite2XL | https://github.com/androidmads/SQLite2XL | Functional | Java | Prateek Aher |  | Gowtham G S | Development in-progress | July-Event | Started with library, but busy with work.
95 | AppCrashTracker | https://github.com/macroday/AppCrashTracker | Functional | Java |  |  | Sharath K S | Available for Development | TBD
96 | Base | https://github.com/thiagokimo/Base/ | Layout | Java |  |  | Sharath K S | Available for Development | TBD
97 | CacheUtilsLibrary | https://github.com/westlinkin/CacheUtilsLibrary | Functional | Java |  |  | Sharath K S | Available for Development | July-Event
98 | FrescoImageView | https://github.com/HomHomLin/FrescoImageView | Functional | Java | Soham | Jaswanth | Kanak Sony | Release to Maven | Intern-IIT
99 | colorpicker | https://github.com/flavienlaurent/colorpicker | Functional | Java | Anshul Goel |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
100 | packagehunter | https://github.com/nisrulz/packagehunter | Functional | Java | Harit Jaiswal |  | Meghna | Release to Maven | Intern-IIT
101 | Bounceview-Android | https://github.com/hariprasanths/Bounceview-Android | Animation | Java | Alpesh kaushal |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
102 | Cosin | https://github.com/NikitaGordia/Cosin | UI | Java | YashRaj Gupta |  | Samuel Abhishekam M | Release to Maven | Intern-IIT
103 | Sherlock | https://github.com/ajitsing/Sherlock | Functional | Java |  |  | Sharath K S | Available for Development | TBD
104 | FancyFacebookBadge-Android | https://github.com/Shashank02051997/FancyFacebookBadge-Android | UI | Java | Sneha Veerakumar |  | Samuel Abhishekam M | Development in-progress | July-Event | Working on library
105 | EasyMoney-Widgets | https://github.com/wajahatkarim3/EasyMoney-Widgets | Tool | Java | Komal Narayan |  | Kanak Sony | Release to Maven | Intern-IIT
106 | PasswordEditText | https://github.com/anshulagarwal06/PasswordEditText | UI | Java | Gowtham G S |  | Sharath K S | Release to Maven | Intern-IIT
107 | ReColor | https://github.com/SIMMORSAL/ReColor | Animation | Java |  |  | Sharath K S | Available for Development | TBD
108 | ArcPageIndicator | https://github.com/BeppiMenozzi/ArcPageIndicator | UI | Java | Yogesh |  | Kanak Sony | Release to Maven | Intern-IIT
109 | SlideActionView | https://github.com/fennifith/SlideActionView | UI | Java | Devang Vijay |  | Gowtham G S | Development in-progress | July-Event | Not Started, busy with placement drive.
110 | emojireactionview |  | UI | Java | Meghna |  | Meghna | Development in-progress | Intern-IIT
111 | RainyView | https://github.com/samlss/RainyView |  | Java |  |  | Sharath K S | Available for Development | TBD
112 | FeedbackDialog | https://github.com/shivasurya/FeedbackDialog |  | Java |  |  | Sharath K S | Available for Development | TBD
113 | android-vertical-stepper-view | https://github.com/liefery/android-vertical-stepper-view |  | Java |  |  | Sharath K S | Available for Development | TBD
114 | OpenWeatherMap-Android-Library | https://github.com/KwabenBerko/OpenWeatherMap-Android-Library |  | Java |  |  | Sharath K S | Available for Development | TBD
115 | JustBar | https://github.com/Hamadakram/JustBar |  | Java |  |  | Sharath K S | Available for Development | TBD
116 | WaveLoading | https://github.com/race604/WaveLoading |  | Java |  |  | Sharath K S | Available for Development | TBD
117 | wearable-reply | https://github.com/klinker24/wearable-reply |  | Java |  |  | Sharath K S | Available for Development | TBD
118 | ReActiveAndroid | https://github.com/ImangazalievM/ReActiveAndroid |  | Java |  |  | Sharath K S | Available for Development | TBD
119 | PowerPreference | https://github.com/AliAsadi/PowerPreference |  | Java |  |  | Sharath K S | Available for Development | TBD

## Mentors_Status
Count of Library Name | Column Labels
Row Labels | Analysis | Stopped | Development in-progress | Release to Maven | Testing in-progress | Available for Development | Code submission to github | Development Completed | Released to HPM | Grand Total
Sharath K S | 11 | 6 | 1 | 3 |  | 28 |  |  |  | 49
Gowtham G S |  |  | 14 |  | 1 |  |  |  |  | 15
Samuel Abhishekam M |  | 1 | 2 | 10 |  |  | 1 |  |  | 14
Kanak Sony |  | 2 | 1 | 8 | [5 empty] | 11
Meghna |  |  | 2 | 7 |  |  |  |  | 1 | 10
Subba Reddy |  | 1 | 2 |  | 2 |  | 2 |  |  | 7
Venkata Sreeni |  |  |  | 4 |  |  | 2 |  |  | 6
Kamal Shree |  | 1 | 2 |  |  |  |  | 2 |  | 5
Kathir |  |  |  | 2 | [5 empty] | 2
Grand Total | 11 | 11 | 24 | 34 | 3 | 28 | 5 | 2 | 1 | 119

## Status_by_Team
SN | Category | Development in-progress | Testing in-progress | Code submission to github | Release to Maven | Released to HPM | Grand Total
1 | IIT-Interns | 1 | 2 | 0 | 26 | 1 | 30
2 | Partners | 1 | 1 | 0 | 1 | 0 | 3
3 | External-Contributors | 4 | 0 | 0 | 0 | 0 | 4
4 | College-Student | 2 | 0 | 1 | 0 | 0 | 3
5 | July-Event | 16 | 0 | 0 | 0 | 0 | 16
6 | Internal Team | 2 | 2 | 3 | 8 | 0 | 15
| Total | 26 | 5 | 4 | 35 | 1 | 71